## PM BURNDOWN CHART
TASKS PLANNED | ACTUAL TASKS REMAINING | DATE(DAYS REMAINING) | ACTUAL TASKS COMPLETED | ACTUAL TASKS PLANNED
29 | 27 | 58 | 1 | 1,2
27 | 26 | 56 | 2,3 | 3
26 | 24 | 54 | 4 | 4
25 | 23 | 51 | 5 | 5
24 | 22 | 48 | 6 | 6
23 | 21 | 41 | 7 | 7
22 | 20 | 40 | 8 | 8
21 | 19 | 38 | 9 | 9
20 | 18 | 36 | 10 | 10
19 | 17 | 33 | 11 | 11
18,17 | 16 | 32 | 12,13 | 12,13
16 | 15 | 30 | 14 | 14
15 | 14 | 29 | 14 | 15
14 | 14 | 28 | 15 | 15,16
13 | 13 | 27 | 16 | 16,17
12 | 13 | 26.5 | 17 | 17,18
11 | 12 | 21 | 17 | 18
10 | 11 | 20 | 18 | 18,19
9 | 10 | 20 | 19 | 20
8 | 8 | 19 | 20,21 | 21
7 | 7 | 17 | 22,23 | 22
6 | 6 | 14 | 24 | 23,24
5 | 5 | 12 | 24 | 25
5 | 4 | 10 | 25,26 | 26
4 | 3 | 8 | 27 | 27
3,2 | 2 | 5 | 28 | 28,29
1 | 1 | 3 | 29 | -
0 | 0 | 0 | - | -
1 | OFFICE LOCATION SETUP
2 | Office Setup
3 | Purchase and set up desks
4 | set up computers
5 | set up wires and networking equipment
6 | set up phones and printers
7 | develop user auth and registration
8 | Customer Booking/Monitoring System Development Requirement
9 | Set up development environment for customer booking
10 | Set up development environment monitoring system
11 | Develop login and registration functionality
12 | Develop booking functionality
13 | Develop payment design
14 | Develop dashboard for all above pointers
15 | Customer Booking/Monitoring System Development
16 | Develop monitoring functionality
17 | Develop reporting functionality
18 | Test and debug customer booking/monitoring system
19 | Set up phones and printers
20 | Add more payment features
21 | Invite customers for promotional event announcement Functionality
22 | Create Marketing Strategy to attract customers in business
23 | Educate employee about the application
24 | Create Marketing Strategy to attract customers in sales,offers
25 | Finish testing, get approval from stake holders
26 | Deploy monitoring application
27 | Employ personnel for operations and tools for office setup completion
28 | Launch Application in systems provided and business
29 | Start a Car Rental Company