## Sprint 15 - User Stories
| EPIC | Issue key | Summary | Customer Review | Status | Status Before | Start Dev | End Dev | Integrated Test | UAT | Available for UAT | UAT (Passed/Failed)
1 | LOGIN | ALPHA1-242 | Disclaimer and Email Setup for new Users | Approved | Done | Done | 2020-03-23 | 2020-04-28 | 2020-04-29 | 2020-05-11 | Yes | Passed
2 | LOGIN | ALPHA1-241 | Implement "Forgot your Organization?" | Approved | Done | Done | 2020-03-23 | 2020-04-28 | 2020-04-29 | 2020-05-11 | Yes | Passed
3 | LOGIN | ALPHA1-290 | New User Password setup | Approved | Done | Done | 2020-03-23 | 2020-04-28 | 2020-04-29 | 2020-05-11 | Yes | Passed
4 | LOGIN | ALPHA1-5 | User Lockout - Wrong password | Approved | Done | Done | 2020-03-23 | 2020-04-28 | 2020-04-29 | 2020-05-11 | Yes | Passed
5 | LOGIN | ALPHA1-2 | User Login | Approved | Done | Done | 2020-03-23 | 2020-04-28 | 2020-04-29 | 2020-05-11 | Yes | Passed
6 | PATIENT - SEARCH | ALPHA1-12 | Search patient in the system | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-01 | 2020-05-04 |  | No
7 | PATIENT - SEARCH | ALPHA1-13 | Select and view the patient Profile from the search result | Approved | UAT | UAT | 2020-03-23 | 2020-05-01 | 2020-05-04 | 2020-07-13 | Yes
8 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-150 | Emergency Contact: Manage Details of a Patient | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-04 | 2020-05-05 |  | No
9 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-71 | Family Physician: Manage data for a patient | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-04 | 2020-05-05 |  | No
10 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-53 | Adding New Patient Basic Details | Approved | INTEGRATED TEST | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-07-17 | No
11 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-123 | Chart Number is auto-incremented by Default | Approved | UAT | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | Yes
12 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-425 | Demographic: Uploading patient's profile photo | Approved | UAT | UAT | 2020-03-23 | 2020-08-21 | 2020-08-21 | 2020-08-21 | Yes
13 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-98 | Demographics: Able to get alerts on duplicate patient registration | Approved | UAT | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | Yes
14 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-72 | Edit Patient details: Change Patient status from demographic screen | Approved | UAT | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | Yes
15 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-122 | Editing Chart Number | Approved | UAT | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | Yes
16 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-141 | Facility/Hospital:Manage data for a patient | Approved | UAT | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | Yes
17 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-156 | Group : Manage data for a patient | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-04 | 2020-05-05 |  | No
18 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-69 | Insurance details: Manage data for a patient | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-04 | 2020-05-05 |  | No
19 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-272 | Manage a Patient Enrollment . | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-08-21 | No
20 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-404 | Patient Details: Add Contact Information | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | No
21 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-59 | Patient details:Edit existing data | Approved | INTEGRATED TEST | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | No
22 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-151 | Preferred Pharmacy: Manage data of a Patient | Approved | UAT | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | Yes
23 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-19 | Primary Physician: Manage data for a patient | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-03-23 | 2020-05-04 | 2020-05-05 |  | No
24 | PATIENT CHART - DEMOGRAPHICS | ALPHA1-76 | Referring Provider: Manage data for a patient | Approved | UAT | UAT | 2020-03-23 | 2020-05-04 | 2020-05-05 | 2020-06-15 | Yes
25 | PATIENT - CPP | ALPHA1-322 | Allergies/Intolerances : Add/Remove columns for Allergies/Intolerances | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-09-03 | Yes
26 | PATIENT - CPP | ALPHA1-319 | Allergies/Intolerances : Adding new Allergies/Intolerances Records | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | Yes
27 | PATIENT - CPP | ALPHA1-321 | Allergies/Intolerances : Deleting existing Allergies/Intolerances Records | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
28 | PATIENT - CPP | ALPHA1-320 | Allergies/Intolerances : Editing existing records | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | No
29 | PATIENT - CPP | ALPHA1-350 | CDM : Add/Remove columns in CDM section | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
30 | PATIENT - CPP | ALPHA1-563 | CDM: Editing existing records | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
31 | PATIENT - CPP | ALPHA1-561 | CPP : Pagination | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
32 | PATIENT - CPP | ALPHA1-351 | CPP item Checkbox Filter | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
33 | PATIENT - CPP | ALPHA1-560 | CPP: Append EMR Notes | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-07-27 | Yes
34 | PATIENT - CPP | ALPHA1-550 | CPP: Default Columns in all tables | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
35 | PATIENT - CPP | ALPHA1-562 | CPP: Launch Icon for Long Notes | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-07-27 | Yes
36 | PATIENT - CPP | ALPHA1-559 | CPP: Residual and Unsupported Information | Approved | In Progress | In Progress | 2020-04-20 |  |  |  | No
37 | PATIENT - CPP | ALPHA1-536 | CPP: Set Layout of CPP tables | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | Yes
38 | PATIENT - CPP | ALPHA1-352 | CPP: View EMR Data upto a certain date. | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
39 | PATIENT - CPP | ALPHA1-247 | Family History: Ability to Add or Remove column in summary session table (to be confirmed) | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | Yes
40 | PATIENT - CPP | ALPHA1-249 | Family History: Adding new Family history Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
41 | PATIENT - CPP | ALPHA1-251 | Family History: Deleting the existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
42 | PATIENT - CPP | ALPHA1-250 | Family History: Editing the existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
43 | PATIENT - CPP | ALPHA1-386 | Health Maintenance : Adding New Screening Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
44 | PATIENT - CPP | ALPHA1-389 | Health Maintenance : Editing the existing Record | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | No
45 | PATIENT - CPP | ALPHA1-395 | Health Maintenance: Add or Remove Column | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
46 | PATIENT - CPP | ALPHA1-390 | Health Maintenance: Deleting any Existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
47 | PATIENT - CPP | ALPHA1-387 | Health Maintenance: Manage Action List | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
48 | PATIENT - CPP | ALPHA1-308 | Immunization : Edit existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | Yes
49 | PATIENT - CPP | ALPHA1-335 | Immunization: add or remove column | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
50 | PATIENT - CPP | ALPHA1-303 | Immunization: Adding new record | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | No
51 | PATIENT - CPP | ALPHA1-577 | Immunization: complete immunization indicator | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
52 | PATIENT - CPP | ALPHA1-305 | Immunization:Delete Existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
53 | PATIENT - CPP | ALPHA1-346 | Medication : Delete existing record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
54 | PATIENT - CPP | ALPHA1-344 | Medication: Adding New Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
55 | PATIENT - CPP | ALPHA1-345 | Medication: Edit existing record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
56 | PATIENT - CPP | ALPHA1-396 | OBS History : Adding new Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | Yes
57 | PATIENT - CPP | ALPHA1-362 | OBS History: Add or Remove Column | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-09-15 | Yes
58 | PATIENT - CPP | ALPHA1-363 | OBS History: Delete the existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
59 | PATIENT - CPP | ALPHA1-1162 | OBS History: Editing existing record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
60 | PATIENT - CPP | ALPHA1-356 | Ongoing Problem : Add new Record | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-04-20 | 2020-06-07 | 2020-06-08 |  | No
61 | PATIENT - CPP | ALPHA1-359 | Ongoing Problem : Chronic Problem Flag | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
62 | PATIENT - CPP | ALPHA1-358 | Ongoing Problem : Delete existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
63 | PATIENT - CPP | ALPHA1-357 | Ongoing Problem : Editing existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-06 | Yes
64 | PATIENT - CPP | ALPHA1-1304 | Ongoing Problem: Adding/Removing Columns | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-09-03 | Yes
65 | PATIENT - CPP | ALPHA1-347 | Past History: Add a new Past History record. | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-09-03 | Yes
66 | PATIENT - CPP | ALPHA1-1045 | Past History: Add/Remove Columns for Past History | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
67 | PATIENT - CPP | ALPHA1-348 | Past History: Delete the existing record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
68 | PATIENT - CPP | ALPHA1-333 | Reminder: Add or Remove columns | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-09-03 | Yes
69 | PATIENT - CPP | ALPHA1-332 | Reminder: Edit the Reminder in CPP | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
70 | PATIENT - CPP | ALPHA1-330 | Reminder: reminders display in CPP | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
71 | PATIENT - CPP | ALPHA1-240 | Risk Factor: Ability to Add and Remove column in the summary table | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
72 | PATIENT - CPP | ALPHA1-243 | Risk Factor: Ability to Delete the existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
73 | PATIENT - CPP | ALPHA1-248 | Risk Factor: Adding new Risk Factor Records | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
74 | PATIENT - CPP | ALPHA1-244 | Risk Factor: Editing the Risk Factor Records | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
75 | PATIENT - CPP | ALPHA1-1161 | Screening Exclusion: Ability to drag and drop column in summary table | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
76 | PATIENT - CPP | ALPHA1-323 | Screening Exclusion: Adding new record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | Yes
77 | PATIENT - CPP | ALPHA1-549 | Screening Exclusion: Delete existing record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
78 | PATIENT - CPP | ALPHA1-343 | Screening Exclusion: Edit existing record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
79 | PATIENT - CPP | ALPHA1-354 | Shortcuts: Form and â€œPrevious Encountersâ€ | Approved | In Progress | In Progress | 2020-04-20 |  |  |  | No
80 | PATIENT - CPP | ALPHA1-328 | Social History: Add or Remove column in summary table | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-21 | Yes
81 | PATIENT - CPP | ALPHA1-325 | Social History: Adding new record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-08-06 | Yes
82 | PATIENT - CPP | ALPHA1-326 | Social History: Deleting existing record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
83 | PATIENT - CPP | ALPHA1-327 | Social History: Editing the Existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
84 | PATIENT - CPP | ALPHA1-340 | Special Needs : Adding a New Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
85 | PATIENT - CPP | ALPHA1-342 | Special Needs: Add/Remove Columns in Special Needs section | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
86 | PATIENT - CPP | ALPHA1-341 | Special Needs: Editing an Existing Record | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-06-26 | Yes
87 | PATIENT CHART - CPP RX | ALPHA1-1318 | Medication: Add or Remove column in summary table | Approved | UAT | UAT | 2020-04-20 | 2020-06-07 | 2020-06-08 | 2020-09-15 | Yes
88 | SCHEDULER | ALPHA1-299 | ..Add Time Slot Template | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-04 | 2020-06-29 | 2020-06-30 |  | No
89 | SCHEDULER | ALPHA1-722 | ..Create Visit Type | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
90 | SCHEDULER | ALPHA1-725 | ..Create/Remove In-Clinic Patient Status | Approved | UAT | UAT | 2020-05-04 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
91 | SCHEDULER | ALPHA1-730 | ..Delete Time Slot | Approved | UAT | UAT | 2020-05-04 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
92 | SCHEDULER | ALPHA1-789 | ..Delete Visit Type | Approved | UAT | UAT | 2020-05-04 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
93 | SCHEDULER | ALPHA1-729 | ..Edit Time Slot | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-04 | 2020-06-29 | 2020-06-30 |  | No
94 | SCHEDULER | ALPHA1-788 | ..Edit Visit Type | Approved | UAT | UAT | 2020-05-04 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
95 | SCHEDULER | ALPHA1-230 | ..Search Free Time slots | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-06-29 | 2020-07-14 | 2020-07-14 |  | No
96 | SCHEDULER | ALPHA1-45 | Able to zoom in/out from the scheduler. | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-04 | 2020-06-29 | 2020-06-30 |  | No
97 | SCHEDULER | ALPHA1-127 | Add time Slot | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-07-14 | No
98 | SCHEDULER | ALPHA1-33 | Customize the scheduler view in month, week, day view and agenda | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-04 | 2020-06-29 | 2020-06-30 |  | No
99 | SCHEDULER | ALPHA1-61 | Drag appointments on scheduler to reschedule. | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-04 | 2020-06-29 | 2020-06-30 |  | No
100 | SCHEDULER | ALPHA1-727 | Edit Time Slot Template | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-08-21 | Yes
101 | SCHEDULER | ALPHA1-800 | Filter Appointments by Status | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-08-05 | Yes
102 | SCHEDULER | ALPHA1-41 | Filter Appointments by Visit Type | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-08-05 | Yes
103 | SCHEDULER | ALPHA1-231 | Health Card Eligibility color code on scheduler | Approved | In Progress | In Progress | 2020-06-15 | 2020-08-24 | 2020-08-24 |  | No
104 | SCHEDULER | ALPHA1-238 | Re-locate the appointment position on the scheduler by "check-in" time | Approved | UAT | UAT | 2020-06-29 | 2020-08-05 | 2020-08-05 | 2020-08-21 | Yes
105 | SCHEDULER | ALPHA1-216 | Restore "Views" on the scheduler | Approved | UAT | UAT | 2020-06-29 | 2020-07-22 | 2020-07-22 | 2020-08-21 | Yes
106 | SCHEDULER | ALPHA1-829 | Scheduler: Add/Save/Delete Views | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-08-21 | Yes
107 | SCHEDULER | ALPHA1-30 | Select filters Provider,Calendar and Appointment to display data on the scheduler | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-04 | 2020-06-29 | 2020-06-30 |  | No
108 | SCHEDULER | ALPHA1-235 | Show/Hide appointment (counts) | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
109 | SCHEDULER | ALPHA1-234 | Show/Hide appointment details on scheduler | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
110 | SCHEDULER | ALPHA1-233 | Show/Hide Time Slots on scheduler | Approved | UAT | UAT | 2020-05-04 | 2020-06-29 | 2020-06-30 | 2020-09-03 | Yes
111 | SCHEDULER - APPOINTMENT | ALPHA1-982 | Add Notes for an Existing Appointment | Approved | UAT | UAT | 2020-04-20 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
112 | SCHEDULER - APPOINTMENT | ALPHA1-16 | Appointment history list on the appointment creation screen | Approved | UAT | UAT | 2020-04-20 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
113 | SCHEDULER - APPOINTMENT | ALPHA1-8 | Cancel Appointment from the scheduler | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-13 | Yes
114 | SCHEDULER - APPOINTMENT | ALPHA1-997 | Change Patient In-Clinic Status (Ellipse option) | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
115 | SCHEDULER - APPOINTMENT | ALPHA1-6 | Change status to No Show | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
116 | SCHEDULER - APPOINTMENT | ALPHA1-67 | Confirm Appointment from the scheduler. | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-09-03 | Yes
117 | SCHEDULER - APPOINTMENT | ALPHA1-11 | Create new appointment for existing and new patient (manual) | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-04-20 | 2020-06-06 | 2020-06-06 | 2020-06-08 | No
118 | SCHEDULER - APPOINTMENT | ALPHA1-66 | Delete Appointment from the scheduler | Approved | UAT | UAT | 2020-04-20 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
119 | SCHEDULER - APPOINTMENT | ALPHA1-214 | Duplicate appointment | Approved | UAT | UAT | 2020-06-29 | 2020-07-15 | 2020-07-15 | 2020-09-03 | Yes
120 | SCHEDULER - APPOINTMENT | ALPHA1-60 | Edit existing appointment details | Approved | UAT | UAT | 2020-04-20 | 2020-06-30 | 2020-07-01 | 2020-07-10 | Yes
121 | SCHEDULER - APPOINTMENT | ALPHA1-993 | Find Next Appointment (Ellipse option) | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
122 | SCHEDULER - APPOINTMENT | ALPHA1-52 | Manual Check-in Appointment | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
123 | SCHEDULER - APPOINTMENT | ALPHA1-334 | Scheduler: Ellipse click for appointment menu Item | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
124 | SCHEDULER - APPOINTMENT | ALPHA1-232 | Search for Existing Appointment | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-31 | No
125 | SCHEDULER - APPOINTMENT | ALPHA1-996 | Undo Check-in (Ellipse option) | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-15 | Yes
126 | SCHEDULER - APPOINTMENT | ALPHA1-63 | View appointment and patient details for a particular appointment. | Approved | UAT | UAT | 2020-04-20 | 2020-06-29 | 2020-06-30 | 2020-07-01 | Yes
127 | SCHEDULER - CARD READER | ALPHA1-23 | Book Appointment - RTHC Swiping Health Card | Approved | In Progress | In Progress | 2020-06-15 | 2020-07-10 | 2020-08-24 |  | No
128 | SCHEDULER - CARD READER | ALPHA1-62 | Booking appointment - Swiping Health Card | Approved | UAT | UAT | 2020-06-15 | 2020-07-10 | 2020-08-24 | 2020-09-15 | Yes
129 | SCHEDULER - CARD READER | ALPHA1-10 | Manual RTHC validation | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-06-15 | 2020-07-10 | 2020-08-24 |  | No
130 | SCHEDULER - CARD READER | ALPHA1-1044 | RTHC Validation with Time Limited FSC | Approved | In Progress | In Progress | 2020-06-15 | 2020-07-10 | 2020-08-24 |  | No
131 | PATIENT CHART - ALERTS | ALPHA1-64 | Setting Alert on scheduler screen & patient Chart | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-05-18 | 2020-07-05 | 2020-07-06 |  | No
132 | PATIENT CHART - APPOINTMENT LIST | ALPHA1-805 | Appointment List : Sort columns of table | Approved | UAT | UAT | 2020-07-06 | 2020-07-08 | 2020-07-09 | 2020-07-14 | Yes
133 | PATIENT CHART - APPOINTMENT LIST | ALPHA1-802 | Reset filter to default settings | Approved | UAT | UAT | 2020-07-06 | 2020-07-08 | 2020-07-09 | 2020-07-14 | Yes
134 | PATIENT CHART - APPOINTMENT LIST | ALPHA1-801 | Search appointments for particular patient as per the date | Approved | UAT | UAT | 2020-07-06 | 2020-07-08 | 2020-07-09 | 2020-07-15 | Yes
135 | PATIENT CHART - APPOINTMENT LIST | ALPHA1-803 | Set current settings as default | Approved | UAT | UAT | 2020-07-06 | 2020-07-08 | 2020-07-09 | 2020-07-15 | Yes
136 | PATIENT CHART - GRAPHS | ALPHA1-1061 | Vitals Graph: Show Graph and Data | Approved | UAT | UAT | 2020-06-30 | 2020-07-09 | 2020-07-09 | 2020-07-15 | Yes
137 | PATIENT - RX | ALPHA1-957 | Rx : Search medication | Approved | UAT | UAT | 2020-07-08 | 2020-07-09 | 2020-07-09 | 2020-08-21 | Yes
138 | PATIENT - RX | ALPHA1-1069 | Rx : Delete existing medication from refill/prescription | Approved | UAT | UAT | 2020-06-29 | 2020-07-31 | 2020-07-31 | 2020-08-06 | Yes
139 | PATIENT - RX | ALPHA1-961 | Rx : Edit Existing prescription | Approved | UAT | UAT | 2020-06-29 | 2020-08-20 | 2020-08-20 | 2020-08-21 | Yes
140 | PATIENT - RX | ALPHA1-958 | Rx : Prescribe new Medication | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-06-29 | 2020-08-20 | 2020-08-20 | 2020-08-21 | No
141 | PATIENT - RX | ALPHA1-918 | RX: re-prescribe the drug for the patient from Current Medication | Approved | UAT | UAT | 2020-06-29 | 2020-07-27 | 2020-07-27 | 2020-07-29 | Yes
142 | PATIENT - RX | ALPHA1-919 | RX: re-prescribe the drug from history | Approved | UAT | UAT | 2020-06-29 | 2020-07-21 | 2020-07-21 | 2020-07-29 | Yes
143 | PATIENT - RX | ALPHA1-910 | Rx: Add favorite Drugs from refill panel | Approved | UAT | UAT | 2020-06-29 | 2020-07-27 | 2020-07-27 | 2020-09-03 | Yes
144 | PATIENT - RX | ALPHA1-921 | RX: Add or remove columns for current medication | Approved | UAT | UAT | 2020-06-29 | 2020-07-14 | 2020-07-14 | 2020-08-21 | Yes
145 | PATIENT - RX | ALPHA1-1288 | Rx: Filter column in Search panel | Approved | UAT | UAT | 2020-06-29 | 2020-07-14 | 2020-07-14 | 2020-08-21 | Yes
146 | PATIENT - RX | ALPHA1-914 | RX: Option to save the prescription by Brand name or Generic Name | Approved | UAT | UAT | 2020-06-29 | 2020-07-27 | 2020-07-27 | 2020-08-21 | Yes
147 | PATIENT - RX | ALPHA1-962 | Rx: Remove column from history | Approved | UAT | UAT | 2020-06-29 | 2020-07-14 | 2020-07-14 | 2020-08-21 | Yes
148 | PATIENT - RX | ALPHA1-920 | RX: Stopped medications are displayed under history tab | Approved | UAT | UAT | 2020-06-29 | 2020-08-04 | 2020-08-04 | 2020-08-21 | Yes
149 | PATIENT - RX | ALPHA1-916 | RX: System display active prescribed medication under Current Medication for the patient | Approved | UAT | UAT | 2020-06-29 | 2020-07-27 | 2020-07-27 | 2020-07-29 | Yes
150 | PATIENT - RX | ALPHA1-912 | Rx: System Prompt Drug alerts | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-06-29 | 2020-09-07 | 2020-09-14 |  | No
151 | PATIENT - RX | ALPHA1-915 | RX: User View the Drug Alert Details by clicking (DF, DD, DA) | Approved | UAT | UAT | 2020-06-29 | 2020-08-20 | 2020-08-20 | 2020-09-15 | Yes
152 | PATIENT - RX | ALPHA1-917 | User should be able to view past medications (history Tab) | Approved | UAT | UAT | 2020-07-20 | 2020-07-27 | 2020-07-27 | 2020-08-21 | Yes
153 | PATIENT - RX | ALPHA1-1070 | Rx: Prescribe medication not in the list | Approved | UAT | UAT | 2020-07-22 | 2020-08-04 | 2020-08-04 | 2020-08-21 | Yes
154 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-972 | Diagnostic Imaging : Add New Note | Approved | UAT | UAT | 2020-06-29 | 2020-07-13 | 2020-07-13 | 2020-07-14 | Yes
155 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-975 | Diagnostic Imaging : Change Request Status | Approved | UAT | UAT | 2020-06-29 | 2020-07-17 | 2020-07-17 | 2020-08-21 | Yes
156 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-969 | Diagnostic Imaging : Create a New Request | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-06-29 | 2020-07-17 | 2020-07-17 |  | No
157 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-979 | Diagnostic Imaging : Create New Task | Approved | UAT | UAT | 2020-06-29 | 2020-08-24 | 2020-08-28 | 2020-08-28 | Yes
158 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-971 | Diagnostic Imaging : Delete Request | Approved | UAT | UAT | 2020-06-29 | 2020-07-13 | 2020-07-13 | 2020-07-15 | Yes
159 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-1071 | Diagnostic Imaging : Document Reconciled to a Requisition | Approved | UAT | UAT | 2020-06-29 | 2020-07-22 | 2020-07-22 | 2020-08-21 | Yes
160 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-1072 | Diagnostic Imaging : Edit Notes | Approved | UAT | UAT | 2020-06-29 | 2020-07-13 | 2020-07-13 | 2020-07-14 | Yes
161 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-970 | Diagnostic Imaging : Edit Request | Approved | UAT | UAT | 2020-06-29 | 2020-07-17 | 2020-07-17 | 2020-07-17 | Yes
162 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-976 | Diagnostic Imaging : Sort Columns of the Table | Approved | UAT | UAT | 2020-06-29 | 2020-07-13 | 2020-07-14 | 2020-07-17 | Yes
163 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-974 | Diagnostic Imaging : View Report | Approved | UAT | UAT | 2020-06-29 | 2020-07-17 | 2020-07-17 | 2020-07-17 | Yes
164 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-1075 | Diagnostic Imaging: Pagination | Approved | UAT | UAT | 2020-06-29 | 2020-07-13 | 2020-07-13 | 2020-08-21 | Yes
165 | PATIENT CHART - DIAGNOSTIC IMAGING | ALPHA1-1074 | Diagnostic Imaging: Record Expansion | Approved | UAT | UAT | 2020-06-29 | 2020-07-13 | 2020-07-13 | 2020-07-14 | Yes
166 | ENCOUNTER - SKETCHING | ALPHA1-964 | Sketching : Create a new sketch | Approved | UAT | UAT | 2020-06-29 | Sep 07,2020 | 2020-09-14 | 2020-09-15 | Yes
167 | ENCOUNTER - SKETCHING | ALPHA1-966 | Sketching : Edit the existing Sketches | Approved | UAT | UAT | 2020-06-29 | Sep 07,2020 | 2020-09-14 | 2020-09-15 | Yes
168 | ENCOUNTER - SKETCHING | ALPHA1-965 | Sketching : View past sketches by date range | Approved | UAT | UAT | 2020-06-29 | 2020-07-14 | 2020-07-14 | 2020-07-14 | Yes
169 | PATIENT - CPP | ALPHA1-1366 | CPP - Medication - Include History | Approved | UAT | UAT | 2020-08-17 | 2020-08-20 | 2020-08-20 | 2020-09-03 | Yes
170 | PATIENT - SEARCH REFERRALS | ALPHA1-1108 | Patient: Search Referral | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
171 | PATIENT - SEARCH REFERRALS | ALPHA1-1100 | Referral : Set Default Search Filter | Approved | To Do | To Do |  |  |  |  | No
172 | PATIENT - SEARCH REFERRALS | ALPHA1-1286 | Referrals: Reset filter to default settings | Approved | To Do | To Do |  |  |  |  | No
173 | PATIENT CHART - REFERRALS | ALPHA1-1095 | Create Outgoing Referrals | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
174 | PATIENT CHART - REFERRALS | ALPHA1-1311 | Edit Outgoing Referral | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
175 | PATIENT CHART - REFERRALS | ALPHA1-1102 | Outgoing Referral : Attach/Remove CPP items | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
176 | PATIENT CHART - REFERRALS | ALPHA1-1293 | Outgoing Referral : Attach/Remove Lab Report | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
177 | PATIENT CHART - REFERRALS | ALPHA1-1105 | Outgoing Referral: Attach/Remove Current and Previous Encounters | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
178 | PATIENT CHART - REFERRALS | ALPHA1-1104 | Outgoing Referral: Attach/Remove Scanned Documents | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
179 | PATIENT CHART - REFERRALS | ALPHA1-1107 | Outgoing Referral: Manage Template | Approved | In Progress | In Progress | 2020-08-11 |  |  |  | No
180 | PATIENT CHART - REFERRALS | ALPHA1-1103 | Outgoing Referral: View Documents Reconciled | Approved | In Progress | In Progress | 2020-08-11 |  |  |  | No
181 | PATIENT CHART - REFERRALS | ALPHA1-1106 | Referral : Create Referral Task | Approved | In Progress | In Progress | 2020-08-11 |  |  |  | No
182 | PATIENT CHART - REFERRALS | ALPHA1-1097 | Referral: Print Acknowledgement Letter | Approved | To Do | To Do |  |  |  |  | No
183 | PATIENT CHART - REFERRALS | ALPHA1-1096 | Referral: Print/Preview Outgoing Referral | Approved | To Do | To Do |  |  |  |  | No
184 | PATIENT CHART - REFERRALS | ALPHA1-1099 | Referral: Set Incoming/Outgoing tab as Default | Approved | To Do | To Do |  |  |  |  | No
185 | PATIENT CHART - REFERRALS | ALPHA1-1098 | Referral: Switch Between Incoming/Outgoing Referrals | Approved | To Do | To Do |  |  |  |  | No
186 | PATIENT CHART - REFERRALS | ALPHA1-1292 | Referrals: Add notes for Outgoing and Incoming Referral | Approved | In Progress | In Progress | 2020-08-11 |  |  |  | No
187 | PATIENT CHART - REFERRALS | ALPHA1-1312 | Remove Outgoing Referral | Approved | In Progress | In Progress | 2020-07-15 |  |  |  | No
188 | ADMIN - AUDIT REPORT | ALPHA1-1456 | Audit Report : Search and View | Approved | INTEGRATED TEST | In Progress | 2020-07-27 | Oct 05,2020 | 2020-10-12 |  | No
189 | PRINT | ALPHA1-1457 | Audit Report : Print | Approved | In Progress | In Progress | 2020-07-27 |  |  |  | No
190 | ADMIN - AUDIT REPORT | ALPHA1-1458 | Audit Report : Download Report | Approved | In Progress | In Progress | 2020-07-27 |  |  |  | No
191 | ADMIN - MANAGE AUTHENTICATION PROFILES | ALPHA1-128 | Authentication Profile | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-27 | 2020-08-20 | 2020-08-20 |  | No
192 | ADMIN - MANAGE LOGIN ACCOUNTS | ALPHA1-136 | Create new user account | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-27 | 2020-09-07 | 2020-09-14 |  | No
193 | ADMIN - MANAGE LOGIN ACCOUNTS | ALPHA1-1520 | Create New Staff when Creating New Account | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-27 | 2020-08-28 | 2020-08-31 |  | No
194 | ADMIN - MANAGE LOGIN ACCOUNTS | ALPHA1-1521 | Edit existing Sign in Account | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-27 | 2020-08-28 | 2020-08-31 |  | No
195 | ADMIN - MANAGE LOGIN ACCOUNTS | ALPHA1-1522 | Change Password | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-27 | 2020-09-07 | 2020-09-14 |  | No
196 | ADMIN - MANAGE LOGIN ACCOUNTS | ALPHA1-1523 | Activate/Deactivate any account | Approved | UAT | UAT | 2020-07-27 | Sep 07,2020 | 2020-09-14 | 2020-09-15 | Yes
197 | ADMIN - MANAGE LOGIN ACCOUNTS | ALPHA1-1525 | Change User Name or Signin Roles | Approved | UAT | UAT | 2020-07-27 | 2020-08-28 | 2020-08-31 | 2020-09-01 | Yes
198 | ADMIN - MANAGE LOGIN ACCOUNTS | ALPHA1-1526 | View Accounts as per existing Organizations | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-27 | 2020-08-28 | 2020-08-31 |  | No
199 | ADMIN - MANAGE ROLES | ALPHA1-1462 | Manage Roles: Add a New Role | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-21 | 2020-08-28 | 2020-08-31 |  | No
200 | ADMIN - MANAGE ROLES | ALPHA1-1463 | Manage Roles: View Roles as per existing Organization | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-11 | 2020-08-28 | 2020-08-31 |  | No
201 | ADMIN - MANAGE ROLES | ALPHA1-1464 | Manage Roles: Pagination | Approved | UAT | UAT | 2020-08-11 | 2020-08-28 | 2020-08-31 | 2020-09-01 | Yes
202 | ADMIN - MANAGE ROLES | ALPHA1-1465 | Manage Roles: Edit an existing Role | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-07-21 | 2020-08-28 | 2020-08-31 |  | No
203 | ADMIN - MANAGE ROLES | ALPHA1-1466 | Manage Roles: Delete an existing Role | Approved | UAT | UAT | 2020-07-21 | 2020-08-28 | 2020-08-31 | 2020-09-01 | Yes
204 | ADMIN - MERGE PATIENT | ALPHA1-1654 | Merge Patients | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-07 | 2020-09-14 |  | No
205 | ENCOUNTER - GROWTH CHART | ALPHA1-1065 | Growth Chart: View Graph and Data | Approved | UAT | UAT | 2020-07-30 | 2020-07-31 | 2020-07-31 | 2020-09-01 | Yes
206 | PRINT | ALPHA1-1066 | Growth Chart: Print Growth Chart | Pending Approval | In Progress | In Progress | 2020-08-11 |  |  |  | No
207 | MY - TEMPLATE BUILDER | ALPHA1-1378 | Print Patient Label from Scheduler | Approved | To Do | To Do |  |  |  |  | No
208 | MY - TEMPLATE BUILDER | ALPHA1-1379 | Print Patient Label from Patient Demographic | Approved | To Do | To Do |  |  |  |  | No
209 | MY - TEMPLATE BUILDER | ALPHA1-1380 | Creating "Label" Templates | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
210 | MY - TEMPLATE BUILDER | ALPHA1-1381 | [Place Holder] : Default value on Template Builder screen | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
211 | MY - TEMPLATE BUILDER | ALPHA1-1382 | Label Template: Preview the Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
212 | MY - TEMPLATE BUILDER | ALPHA1-1386 | Encounter Template: Create/Edit Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
213 | MY - TEMPLATE BUILDER | ALPHA1-1387 | Encounter Template: Preview Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
214 | MY - TEMPLATE BUILDER | ALPHA1-1388 | Encounter Template : Encounter and Custom Section Display Rules | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
215 | MY - TEMPLATE BUILDER | ALPHA1-1389 | Encounter Template : Add/Edit/Disable Sections in All Section table | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
216 | MY - TEMPLATE BUILDER | ALPHA1-1390 | Encounter Template : Add/Remove Section from Custom Section table | Approved | In Progress | In Progress | 2020-08-24 |  |  |  | No
217 | MY - TEMPLATE BUILDER | ALPHA1-1391 | Encounter Template : Custom Section Encounter Note Area Selection | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
218 | MY - TEMPLATE BUILDER | ALPHA1-1392 | Encounter Template : Disable/Enable Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
219 | MY - TEMPLATE BUILDER | ALPHA1-1394 | Label Templates : are shared across the system | Approved | To Do | To Do |  |  |  |  | No
220 | MY - TEMPLATE BUILDER | ALPHA1-1395 | Label Template: Enable/Disable the Label Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
221 | MY - TEMPLATE BUILDER | ALPHA1-1524 | Encounter Template : Collapse/Expand Table and Pagination | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
222 | MY - TEMPLATE BUILDER | ALPHA1-1564 | Template Builder: Default view | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
223 | MY - TEMPLATE BUILDER | ALPHA1-1565 | Review of System Template Add New | Approved | In Progress | In Progress | 2020-09-07 |  |  |  | No
224 | MY - TEMPLATE BUILDER | ALPHA1-1566 | Review of System Template Edit Template | Approved | In Progress | In Progress | 2020-09-07 |  |  |  | No
225 | MY - TEMPLATE BUILDER | ALPHA1-1567 | Review of System Template Delete Template | Approved | In Progress | In Progress | 2020-09-07 |  |  |  | No
226 | MY - TEMPLATE BUILDER | ALPHA1-1568 | Review of System Template Add New System | Approved | In Progress | In Progress | 2020-09-22 |  |  |  | No
227 | MY - TEMPLATE BUILDER | ALPHA1-1569 | Review of System Template Edit System | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
228 | MY - TEMPLATE BUILDER | ALPHA1-1570 | Review of System Template Delete System | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
229 | MY - TEMPLATE BUILDER | ALPHA1-1573 | Review of System Template Add New Symptom | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
230 | MY - TEMPLATE BUILDER | ALPHA1-1574 | Review of System Template Edit Symptom | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
231 | MY - TEMPLATE BUILDER | ALPHA1-1575 | Review of System Template Delete Symptom | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
232 | MY - TEMPLATE BUILDER | ALPHA1-1576 | Physical Examination Template Add New | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
233 | MY - TEMPLATE BUILDER | ALPHA1-1577 | Physical Examination Template Edit Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
234 | MY - TEMPLATE BUILDER | ALPHA1-1579 | Physical Examination Template Delete Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
235 | MY - TEMPLATE BUILDER | ALPHA1-1580 | Physical Examination Template Add New System | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
236 | MY - TEMPLATE BUILDER | ALPHA1-1581 | Physical Examination Template Edit System | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
237 | MY - TEMPLATE BUILDER | ALPHA1-1582 | Physical Examination Template Delete System | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
238 | MY - TEMPLATE BUILDER | ALPHA1-1583 | Physical Examination Template Add New Symptom | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
239 | MY - TEMPLATE BUILDER | ALPHA1-1584 | Physical Examination Template Edit Symptom | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
240 | MY - TEMPLATE BUILDER | ALPHA1-1585 | Physical Examination Template Delete Symptom | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
241 | MY - TEMPLATE BUILDER | ALPHA1-1587 | Review of System Template Default View | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
242 | MY - TEMPLATE BUILDER | ALPHA1-1588 | Review of System Template Add New Template using ' Save As ' | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
243 | MY - TEMPLATE BUILDER | ALPHA1-1649 | Create Correspondence Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
244 | MY - TEMPLATE BUILDER | ALPHA1-1650 | Correspondence Template: Edit | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
245 | MY - TEMPLATE BUILDER | ALPHA1-1651 | Label Template: Edit | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
246 | MY - TEMPLATE BUILDER | ALPHA1-1652 | Correspondence Template: Preview | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
247 | MY - TEMPLATE BUILDER | ALPHA1-1653 | Correspondence Template: Disable/Enable Template | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
248 | PATIENT CHART - APPOINTMENT LIST | ALPHA1-1674 | Ellipse for Add/Remove Column | Approved | UAT | UAT | 2020-07-27 | 2020-08-04 | 2020-08-04 | 2020-09-03 | Yes
249 | MY - TEMPLATE BUILDER | ALPHA1-1850 | Physical Examination Template - Default View | Approved | In Progress | To Do | 2020-10-05 |  |  |  | No
250 | PRINT | ALPHA1-1101 | Incoming Referral: View & Print Incoming Referral Document | Approved | To Do | To Do |  |  |  |  | No
251 | PRINT | ALPHA1-804 | PRINT - Print appointments of particular patient | Approved | To Do | To Do |  |  |  |  | No
252 | PRINT | ALPHA1-353 | PRINT - Ability to print / preview the data on CPP chart | Approved | To Do | To Do |  |  |  |  | No
253 | PRINT | ALPHA1-73 | Print Labels from the Demographic page. | Approved | To Do | To Do |  |  |  |  | No
254 | PRINT | ALPHA1-31 | Print patient label from scheduler | Approved | To Do | To Do |  |  |  |  | No
255 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1181 | Create Internal Provider ( Details tab) | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-07 | 2020-09-14 |  | No
256 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1257 | Create new external provider | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-07 | 2020-09-14 |  | No
257 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1259 | Create new external organization | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-08-28 | 2020-08-31 |  | No
258 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1266 | Delete Int/Ext Organizations | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-08-28 | 2020-08-31 |  | No
259 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1680 | Edit- Internal Provider | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-22 | 2020-09-23 |  | No
260 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1779 | Creating Provider/Organization under a selected Organization | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-07 | 2020-09-14 |  | No
261 | FAX | ALPHA1-978 | Diagnostic Imaging : Fax | Pending Approval | In Progress | In Progress | 2020-08-24 |  |  |  | No
262 | PRINT | ALPHA1-977 | Diagnostic Imaging :Print | Pending Approval | In Progress | In Progress | 2020-08-24 |  |  |  | No
263 | MY - DOCUMENT LIBRARIES | ALPHA1-968 | Sketches :Document Libraries: Import Sketch Document | Pending Approval | To Do | In Progress |  |  |  |  | No
264 | ENCOUNTER - ENCOUNTER | ALPHA1-967 | Sketching : Remove Sketches | Approved | In Progress | In Progress | 2020-08-24 |  |  |  | No
265 | PRINT | ALPHA1-304 | PRINT- Immunization: Immunization Card Record population from CPP section | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-22 | 2020-09-23 |  | No
266 | HOME - PREFERENCES | ALPHA1-236 | ..Setting default point of time on scheduler | Approved | In Progress | In Progress | 2020-08-24 |  |  |  | No
267 | ADMIN - PERMISSIONS | ALPHA1-135 | Grant/Remove Operation for Manage Organization-Provider Information | Approved | To Do | To Do |  |  |  |  | No
268 | ADMIN - PERMISSIONS | ALPHA1-1838 | Grant/Remove Operation for Patient Management - Patient Demographics | Approved | To Do | To Do |  |  |  |  | No
269 | ADMIN - PERMISSIONS | ALPHA1-1843 | Grant/Remove Operation for Patient Management â€“ Chronic Disease Management | Approved | To Do | To Do |  |  |  |  | No
270 | ADMIN - PERMISSIONS | ALPHA1-130 | Grant/Remove Operation for Manage Organization-Manage Payer and Payment Plan | Approved | To Do | To Do |  |  |  |  | No
271 | ADMIN - PERMISSIONS | ALPHA1-132 | Grant/Remove Data - for Patient Management - Patient Medical Record | Approved | To Do | To Do |  |  |  |  | No
272 | ADMIN - PERMISSIONS | ALPHA1-133 | Grant/Remove Operation/Data for Patient Management - Encounter Management | Approved | To Do | To Do |  |  |  |  | No
273 | ADMIN - PERMISSIONS | ALPHA1-1677 | Grant/Remove Operation for Bill Management-Claim and Payment Management | Approved | To Do | To Do |  |  |  |  | No
274 | ADMIN - PERMISSIONS | ALPHA1-1699 | Grant/Remove Operation for Module Access-Patient Management | Approved | To Do | To Do |  |  |  |  | No
275 | ADMIN - PERMISSIONS | ALPHA1-1700 | Grant/Remove Operation for Module Access-Billing Management | Approved | To Do | To Do |  |  |  |  | No
276 | ADMIN - PERMISSIONS | ALPHA1-1701 | Grant/Remove Operation for Module Access-Miscellaneous | Approved | To Do | To Do |  |  |  |  | No
277 | ADMIN - PERMISSIONS | ALPHA1-1706 | Grant/Remove Operation for Module Access-Manage Organization | Approved | To Do | To Do |  |  |  |  | No
278 | ADMIN - PERMISSIONS | ALPHA1-1707 | Grant/Remove Operation for Module Access-Schedule Management | Approved | To Do | To Do |  |  |  |  | No
279 | ADMIN - PERMISSIONS | ALPHA1-1708 | Grant/Remove Operation for Module Access-Report | Approved | To Do | To Do |  |  |  |  | No
280 | ADMIN - PERMISSIONS | ALPHA1-1709 | Grant/Remove Operation for Bill Management-Fee Schedule Management | Approved | To Do | To Do |  |  |  |  | No
281 | ADMIN - PERMISSIONS | ALPHA1-1713 | Grant/Remove Operations for Miscellaneous-Document Management | Approved | To Do | To Do |  |  |  |  | No
282 | ADMIN - PERMISSIONS | ALPHA1-1714 | Read/Write Data for Miscellaneous-Task Management | Approved | To Do | To Do |  |  |  |  | No
283 | ADMIN - PERMISSIONS | ALPHA1-1715 | Common Feature : View Existing Exception (table format) | Approved | To Do | To Do |  |  |  |  | No
284 | ADMIN - PERMISSIONS | ALPHA1-1716 | Common Feature : Add New Exception | Approved | To Do | To Do |  |  |  |  | No
285 | ADMIN - PERMISSIONS | ALPHA1-1717 | Common Feature : Delete Exception | Approved | To Do | To Do |  |  |  |  | No
286 | ADMIN - PERMISSIONS | ALPHA1-1718 | Common Feature : Edit Exception | Approved | To Do | To Do |  |  |  |  | No
287 | ADMIN - PERMISSIONS | ALPHA1-1830 | Grant/Remove Operation for Manage Organization â€“ Manage Login | Approved | To Do | To Do |  |  |  |  | No
288 | ADMIN - PERMISSIONS | ALPHA1-1831 | Grant/Remove Operation for Manage Organization â€“ Manage Organizations | Approved | To Do | To Do |  |  |  |  | No
289 | ADMIN - PERMISSIONS | ALPHA1-1832 | Grant/Remove Operation for Manage Organization â€“ Manage Patient Groups | Approved | To Do | To Do |  |  |  |  | No
290 | ADMIN - PERMISSIONS | ALPHA1-1833 | Grant/Remove Operation for Manage Organization â€“ Manage Providers | Approved | To Do | To Do |  |  |  |  | No
291 | ADMIN - PERMISSIONS | ALPHA1-1837 | Grant/Remove Data for Manage Organization- Organizational Data | Approved | To Do | To Do |  |  |  |  | No
292 | ADMIN - PERMISSIONS | ALPHA1-1842 | Grant/Remove Operation for Patient Management â€“ Manage Referral Letters and Templates | Approved | To Do | To Do |  |  |  |  | No
293 | ADMIN - PERMISSIONS | ALPHA1-1844 | Grant/Remove Operation for Lab Management â€“ Lab Report | Approved | To Do | To Do |  |  |  |  | No
294 | ADMIN - PERMISSIONS | ALPHA1-1845 | Grant/Remove Operation for Lab Management â€“ Lab Order | Approved | To Do | To Do |  |  |  |  | No
295 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1250 | Creating new internal organization | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-08-28 | 2020-08-31 |  | No
296 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1260 | Search provider and Organizations | Approved | INTEGRATED TEST | In Progress | 2020-08-24 | Oct 05,2020 | 2020-10-12 |  | No
297 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1275 | Delete Internal/External Provider | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-07 | 2020-09-14 |  | No
298 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1281 | Create Internal Provider ( Preferred Pharmacy tab) | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-07 | 2020-09-14 |  | No
299 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1518 | Edit - Internal Organization | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-08-28 | 2020-08-31 |  | No
300 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1519 | Edit - External Organization | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-08-28 | 2020-08-31 |  | No
301 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1666 | Create Internal Provider (Practice Location) | Approved | In Progress | In Progress | 2020-08-24 |  |  |  | No
302 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1670 | Edit - External Provider | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-08-24 | 2020-09-07 | 2020-09-14 |  | No
303 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-1778 | Print Internal Provider Information | Approved | In Progress | In Progress | 2020-09-07 |  |  |  | No
304 | FAX | ALPHA1-978 | Diagnostic Imaging : Fax | Pending Approval | In Progress | In Progress | 2020-09-07 |  |  |  | No
305 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-99 | Create New Resources | Approved | In Progress | In Progress | 2020-09-07 |  |  |  | No
306 | PATIENT - CPP | ALPHA1-2232 | Display Items Order for all the Tables in the CPP section | Approved | UAT | UAT | 2020-09-22 | 2020-09-22 | 2020-09-23 | 2020-10-01 | Yes
307 | PRINT | ALPHA1-43 | PRINT - Print day sheets | Pending Approval | To Do | To Do |  |  |  |  | No
308 | PRINT | ALPHA1-84 | PRINT - Demographics: Print Patient Information | Pending Approval | To Do | To Do |  |  |  |  | No
309 | ORGANIZATION - MANAGE PROVIDER | ALPHA1-2206 | Adding Roles for Internal Provider | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-09-22 | 2020-09-23 | 2020-10-01 |  | No
310 | PATIENT CHART - CPP | ALPHA1-2585 | Past History: Edit the existing record | Approved | UAT | INTEGRATED TEST | 2020-09-22 | 2020-09-23 | 2020-10-01 | 2020-10-12 | No
311 | CHANGE REQUEST | ALPHA1-2601 | ORGANIZATION - MANAGE PROVIDER: Provider/Org Search | Approved | INTEGRATED TEST | INTEGRATED TEST | 2020-09-22 | 2020-09-23 | 2020-10-01 |  | No
312 | CHANGE REQUEST | ALPHA1-2389 | Implement "Forgot your Organization?" (missing rule) | Approved | UAT | UAT | 2020-09-22 | 2020-09-22 | 2020-09-23 | 2020-10-01 | Yes
Note on C104: Andrea Cavalheiro: Identified in the Integrated Test. It was already implemented.
Note on J106: Andrea Cavalheiro: only UI
Note on J130: Andrea Cavalheiro: Only UI
Note on J133: Andrea Cavalheiro: Only UI

## Burndown - User Stories (Sp 15)
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | End | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16
Total User Stories | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 985 | 980 | 980
Ideal Burndown | 985 | 886.5 | 788 | 689.5 | 591 | 492.5 | 394 | 295.5 | 197 | 98.5 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Development | 985 | 961 | 961 | 883 | 864 | 863 | 863 | 858 | 819 | 806 | 793 | 785 | 761 | 757 | 751 | 718
Remaining User Stories | 985 | 915 | 911 | 887 | 832 | 795 | 755 | 699 | 643 | 621 | 597 | 581 | 564 | 551 | 516 | 477
Remaining Integrated Test | 985 | 985 | 985 | 980 | 962 | 962 | 900 | 900 | 860 | 841 | 829 | 824 | 804 | 791 | 787 | 785
Ideal Points per day | 98.5 | 98.5 | 98.5 | 98.5 | 98.5 | 98.5 | 98.5 | 98.5 | 98.5 | 98.5 | 0 | 0 | 0 | 0 | 0
In Progress | 24 | 0 | 78 | 19 | 1 | 0 | 5 | 39 | 13 | 13 | 8 | 24 | 4 | 6 | 33
Integrated Test | 0 | 0 | 5 | 18 | 0 | 62 | 0 | 40 | 19 | 12 | 5 | 20 | 13 | 4 | 2
US Recorded | 70 | 4 | 24 | 55 | 37 | 40 | 56 | 56 | 22 | 24 | 16 | 17 | 13 | 35 | 39